Proposed Preparatory Process for Regional IYRP Groups

Objectives

The campaign to promote the IYRP for the FAO COAG 2020 has been supported by a very strong, vibrant, active and worldwide network of more than 150 civil society, public and private sector institutions, organizations, cooperatives and associations, as well as at least 25 governments. This network could be leveraged even more strongly in the run-up to the UN General Assembly in October 2021, by creating regional nodes of communication and cooperation, supported by the ISG (IYRP International Support Group), FAO and others at the global level, and by the Government of Mongolia, Mongolian National IYRP Support Group, and other active supporters at the regional and national levels.

The ultimate goal of creating Regional IYRP Support Groups (RISGs) is to campaign for the designation of IYRP by the United Nations for 2026, with two immediate objectives:

- To expand the network of supporting organizations and governments in the regions and at country and local levels by continuing to raise awareness; and

- Assuming that UNGA does designate the IYRP, by working with the ISG, FAO, the Government of Mongolia and other global supporters, to prepare suggestions and guidance for IYRP planning and implementation in their respective regions (regional action plans).

In addition to having strong regional ties and knowledge of stakeholders, RISGs can communicate better in their respective region’s languages.  They can ensure a strong and equitable participatory process for all supporting organizations. Furthermore, as the list of supporting organizations and countries grows, it will be more efficient to create regional nodes than trying to create a global center. The role of the ISG, FAO, and the Government of Mongolia will continue to be important in ensuring a coordinated approach across the regions. The Joint International Grassland Congress (IGC) and International Rangeland Congress (IRC) in October 2021 will provide an opportunity to ensure coordination among the RISGs, as well as to validate and peer review the regional action plans.

Therefore, at least four major milestones are foreseen:

- FAO Council (30 Nov–4 Dec 2020)

- FAO Conference (June/July 2021)

- UN General Assembly (14–30 September 2021)

- IRC and IGC Joint Congress (23–29 October 2021)

The RISGs will be based on the “regional working groups” already proposed by the ISG for the purpose of engaging with the Joint IRC and IGC. Their immediate focus will be on these four milestones. Membership will be wider than that envisaged for the Joint Congress. Their continued functioning in 2022 and beyond will be a function of need, and most likely subject to a revision in mandate.

Expected outcomes & activities

By end of November 2020 =

Outcome: Expansion in the number of supporting governments and organizations and of the concrete commitments for support (financial and in-kind)

Activities: lobbying at the level of governments and regional bodies EU, League of Arab States etc.; promotion and communications activities; development of communications materials such as documentaries, videos to be shared on IYRP Online Booth (www.iyrp.info); development of content to be shared on IYRP Online Booth; Identifying and reaching out organizations at regional/national levels.

By June 2021 =

Outcome: Expansion in the number of supporting governments and organizations and of the concrete commitments for support (financial and in-kind); endorsement of IYRP Proposal by the FAO Conference.

Activities: lobbying at the level of governments and regional bodies such as EU, League of Arab States etc.; promotion and communications activities; developing and conducting an online campaign prior to the conference (if needed); be available to respond to requests coming from countries and delegates at the FAO Conference; participating in and/or organizing (an) awareness event(s) in Rome (such as side events etc.) with allocating resources for this purpose, if physical meetings are held.

By UNGA in September 2021 =

Outcome: Expansion in the number of supporting governments and organizations and of the concrete commitments for support (financial and in-kind); endorsement of IYRP Proposal by the UNGA

Activities: lobbying at the level of governments and regional bodies such as EU, League of Arab States etc.; promotion and communications activities; developing and conducting an online campaign prior to the General Assembly; participating in and/or organizing (an) awareness event(s) in New York (such as side events, seminars for delegates, exhibits, movie screenings, etc.) with allocating resources for this purpose, if physical meetings are held.

By the Joint Congress in October 2021 = Prepare draft IYRP regional action plans, and be represented at the Congress for discussion of these plans; support Congress resolutions. The Congress Secretariat and delegates will be kept appraised of the work of the RISGs through regular updates to the Congress website as well as to the IYRP “Online Booth” website.

Organization

By the end of August 2020, members of the IRC Continuing Committee (CC), the IGC CC and the ISG had been invited to volunteer to sit in one of 10 following “regional working groups”. In October 2020, all other supporting organizations and governments will be invited to expand these into Regional IYRP Support Groups, with the aim of having at least one person per country in each of the RISGs.

Regional categories for the RISG:

- East Asia

- Central Asia and Mongolia

- South Asia

- Oceania

- North Africa and Middle East

- Eastern and Southern Africa

- West and Central Africa

- Europe and Arctic

- North America (Canada, USA and Mexico)

- South and Central America

The ISG will initially convene these groups (one by one) to launch their work, but the RISG members will elect their own chairs and communication teams, and decide on their own strategies and internal deadlines. However, it is expected that each group will focus on at least four immediate tasks:

- To review the “12-monthly themes” and the IYRP Open Flyer as developed by the ISG in 2018, in order to update it and adapt it to the region

- To manage the regional page of the IYRP Online Booth, including identifying and uploading information, and adding more supporting organizations

- To review and help finalize the Regional Papers being developed by the Congress Authors, in time for the deadline of Full Paper Submission of 30 November 2020 (if necessary).

- Respond to any requests as needed in the run-up to the FAO Council session in November/December 2020.

The RISGs will regularly report to the ISG on their progress, and bring new ideas to share.