## Unit Priorities Tracker - SPLS
Item | Details | Mission Area | Point of Contact | Priority | Last Status | Done | Start Date | Expected Date | Completion Date | Level
SPLS | [9 empty] | Level 0
Priority Category 1 | Research Portfolio Enhancement | Research | [7 empty] | Level 1
Priority Group 1A | Grow Regional and National Impact | Research | A. Elizabeth Arnold |  | Doing |  | 2023-01-01 |  |  | Level 2
a. | Improve marketing of faculty, staff, infrastructure and student strengths |  |  | High | Doing |  | 2023-01-01 |  |  | Level 3
b. | Hold faculty/all hands retreat for growth/discussion |  |  | Medium | Doing |  | 2023-01-01 |  |  | Level 3
Priority Group 1B | Expansion of Excellence in Arid Lands Agriculture and Related Areas | Research | A. Elizabeth Arnold |  | Doing |  |  |  |  | Level 2
a. | Promote industry partnerships |  |  | High |  |  | 2023-01-01 |  |  | Level 3
b. | Expand internships and training partnerships |  |  | High |  |  | 2023-01-01 |  |  | Level 3
c. | Promote new collaborative, large-scale grants |  |  | Medium |  |  | 2023-01-01 |  |  | Level 3
Priority Group 1C | Faculty Recruitment: FY2024 | Land Grant | David Galbraith |  | Doing |  | 2023-01-01 |  |  | Level 3
a. | We have provided to CALS Administration a recruitment plan for FY2024 |  |  | High | Complete | TRUE |  |  | 2023-02-16 | Sublevel
Priority Category 2 | Enrollment Growth & Quality Enhancement | Instruction | [7 empty] | Level 1
Priority Group 2A | Existing Curriculum | Instruction | [7 empty] | Level 2
a. | Submit collaborative USDA proposal with UA-Yuma to enhance future undergraduate enrollment |  | Tanya Hodges | Medium | Complete | TRUE | 2022-11-01 |  | 2022-12-31 | Level 3
b. | Refresh existing General Education courses and propose new ones |  | Various | Medium | Doing |  | 2021-07-01 | 2024-06-30 |  | Level 3
c. | Address issues of integrating and sequencing experiential learning into our undergraduate major curricula |  | Various | Medium | Doing |  | 2021-07-01 | 2024-06-30 |  | Level 3
d. | Co-leadership of interdepartmental Microbiology program |  | Various | Medium | Doing |  | 2021-05-01 | 2024-06-30 |  | Level 3
e. | Implement measures to stabilize/restore declining enrollment in Microbiology |  | Various | Medium | Queued |  | 2023-01-01 |  |  | Level 3
f. | Develop high-quality online versions of existing courses |  | Various | Medium | Doing |  | 2020-01-01 |  |  | Level 3
Priority Group 2B | New Curriculum | Instruction | [7 empty] | Level 2
a. | Submit proposal for an undergraduate certificate in Cannabis, in collaboration with Biosystems Engineering |  | Samantha Orchard | Medium | Doing |  | 2023-02-01 | 2023-04-01 |  | Level 3
b. | Submit proposal for students in the Urban Horticulture emphasis within the Sustainable Plant Systems major to complete an Accelerated Masters Program and earn a Masters of Landscape Architecture, in collaboration with CAPLA |  | Samantha Orchard | Medium | Doing |  | 2023-02-01 | 2023-04-01 |  | Level 3
c. | Establish new track under Microbiology major that has a focus outside of medical microbiology, to attract additional students |  | Various | Medium | Queued |  | 2023-03-01 |  |  | Level 3
d. | Maintain an increased alertness of the effects of "Black Swan" events on education: most notably, adjust to the impact of AI (ChatGTP, and its intellectual progeny) on our educational activities |  | David Galbraith | High | Queued |  | 2023-03-01 |  |  | Level 3
Priority Group 2C | Local, Regional, and International Programs | [8 empty] | Level 3
a. | Complete articulation process for Applied Biotechnology dual degree program at Kozybayev University in Kazakhstan | Instruction | Samantha Orchard | High | Doing |  | 2022-05-01 | 2023-03-01 |  | Level 3
b. | Plan instructional staffing for Applied Biotechnology dual degree program at Kozybayev University in Kazakhstan | Instruction | Samantha Orchard | High | Doing |  | 2023-01-01 | 2023-09-01 |  | Level 3
c. | Adapt courses for remote delivery and co-teaching for Applied Biotechnology dual degree program at Kozybayev University in Kazakhstan | Instruction | Samantha Orchard | Medium | Queued |  | 2023-09-01 | 2024-07-03 |  | Level 3
d. | Participate in discussions about launching other SPLS dual degree programs (Agronomy and Plant Health) at Kozybayev University in Kazakhstan | Instruction | Samantha Orchard | Medium | Paused |  | 2023-03-01 | 2023-06-01 |  | Level 3
e. | Participate in discussions about launching educational programs in Morocco | Research/Instruction | Various | Medium | Queued |  | 2023-01-01 |  |  | Level 3
Priority Category 3 | Engagement & Stakeholder Outreach | Extension | [7 empty] | Level 1
Priority Group 3A | Specialist Recruitment |  | Ursula Schuch | High | Doing |  |  |  |  | Level 2
Priority | We are currently searching for two Specialists | [8 empty] | Level 3
Priority Group 3B | Specialist Recruitment Future Request |  |  | High | Queued |  |  |  |  | Level 2
Priority | We have provided CALS Administration a Recruitment Plan for FY2024 |  | Ursula Schuch | [6 empty] | Level 3
Priority Group 3C | Publicize the Mission and Accomplishments of SPLS |  |  | High | Doing |  |  |  |  | Level 3
Priority | Refresh the SPLS Website | Outreach | Various | High | Doing |  |  |  |  | Level 3
Priority | Participate in local/regional events: outreach | Outreach | Various | Medium | Doing |  |  |  |  | Level 3
Priority | Faculty participation in local municipalities/organizations | Outreach | Various | Medium | Doing |  |  |  |  | Level 3
Priority Category 4 | Future Program Development | Program | [7 empty] | Level 1
Priority Group 4A | Work with CALS Development Office Liaison to Secure Funding |  | David Galbraith | High | Doing |  | 2023-01-01 |  |  | Level 2
a. | Secure funding for undergraduate and graduate scholarships | [8 empty] | Level 3
b. | Identify internship locations for undergraduate majors | [8 empty] | Level 3
c. | Identify funding sources for support of faculty positions and operating expenses | [8 empty] | Level 3
Priority Group 4B | [9 empty] | Level 2
Priority | [9 empty] | Level 3
Priority Category 5 |  | Infrastructure | [7 empty] | Level 1
Priority Group 5A | New Initiatives:planning | [8 empty] | Level 2
a. | Establish an annual personnel retreat to discuss and establish priorities in a rapidly changing world |  | All | High | Doing |  | 2023-03-01 |  |  | Level 3
b. | Coordinate initiative planning with the hiring of a Permanent Director |  | All | High | Doing |  | 2023-03-01 |  |  | Level 3
Priority Group 5B | Deferred Maintenance | [8 empty] | Level 2
a. | Appointed March Orbach to develop a CALS-wide initiative for deferred maintenance using Marley as the model |  | Marc Orbach | High | Complete | TRUE | 2023-03-01 |  | 2023-02-16 | Level 3
b. | Identify cooperating units and their representatives |  |  | High | Queued |  | 2023-03-01 |  |  | Level 3
Level 3